## Sheet1
Iteration #1	Feature	Feature	Feature	Feature
2022 Oct 3rd
Features in scope	Start a quiz	Create a document	Upload document
Features implemented	Start a quiz	Create a document
Features in deficit this Iteration	Upload document
Iteration Comments & Summary	Quiz functionality has been implement on client side, however communication between client and server is not yet set up. All features in this iteration are to be refined in future iterations.

Iteration #2
2022 Dec 3rd
Features in scope	Start a quiz	Review Document	Create a document	Upload document	User account creation
Features implemented	Start a quiz	Review Document
Features in deficit this Iteration	Create a document	Upload document	User account creation
Iteration Comments & Summary	For this iteration I have focused on moving to the Blazor framework for the project.

Iteration #3

Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary

Iteration #4
2023 Feb 12th
Features in scope	Android client	Web api (User file store)
Features implemented
Features in deficit this Iteration	Android client	Web api (User file store)
Iteration Comments & Summary	This iteration aims have been to create an android client which is still on going. Beyond this a web api for users to sign in on both clients which will later allow for file storage.

Iteration #5
2023 Mar 5th
Features in scope	User account CRUD	Synonym API functionality	Translation API functionality	Addtitional quiz functionality (Regex)	Restful API for user files	Android client
Features implemented	User account CRUD	Synonym API functionality	Translation API functionality	Addtitional quiz functionality (Regex)	Restful API for user files
Features in deficit this Iteration	Android client
Iteration Comments & Summary	For this iteration many features have been introduced to improve the web-client functionality. The android client has been improved and can now complete some of the basic functions seen in the web-client. A new Restful API has been created to allow users to store custom notes.

Iteration #6
Date of milestone
Features in scope
Features implemented
Features in deficit this Iteration
Iteration Comments & Summary