## Sheet1
Iteration #1 | Feature | Feature | Feature | Feature
2022 Oct 3rd
Features in scope | Start a quiz | Create a document | Upload document
Features implemented | Start a quiz | Create a document
Features in deficit this Iteration | Upload document
Iteration Comments & Summary | Quiz functionality has been implement on client side, however communication between client and server is not yet set up. All features in this iteration are to be refined in future iterations.
Iteration #2
2022 Dec 3rd
Features in scope | Start a quiz | Review Document | Create a document | Upload document | User account creation
Features implemented | Start a quiz | Review Document
Features in deficit this Iteration | Create a document | Upload document | User account creation
Iteration Comments & Summary | For this iteration I have focused on moving to the Blazor framework for the project.
Iteration #3
2023 Dec 18th
Features in scope | Document creation | User account creation
Features implemented
Features in deficit this Iteration | Document creation | User account creation
Iteration Comments & Summary | Iteration focused on problem solving existing code
Iteration #4
2023 Feb 12th
Features in scope | Android client | Web api (User file store)
Features implemented
Features in deficit this Iteration | Android client | Web api (User file store)
Iteration Comments & Summary | This iteration aims have been to create an android client which is still on going. Beyond this a web api for users to sign in on both clients which will later allow for file storage.
Iteration #5
2023 Mar 5th
Features in scope | User account CRUD | Synonym API functionality | Translation API functionality | Additional quiz functionality (Regex) | Restful API for user files | Android client
Features implemented | User account CRUD | Synonym API functionality | Translation API functionality | Additional quiz functionality (Regex) | Restful API for user files
Features in deficit this Iteration | Android client
Iteration Comments & Summary | For this iteration many features have been introduced to improve the web-client functionality. The android client has been improved and can now complete some of the basic functions seen in the web-client. A new Restful API has been created to allow users to store custom notes.
Iteration #6
2023 Mar 26th
Features in scope | Regex partial solutions | Restful web service (user notes) | User notes CRUD (with restful service) | User note progress tracking
Features implemented | Regex partial solutions | Restful web service (user notes) | User notes CRUD (with restful service) | User note progress tracking
Features in deficit this Iteration
Iteration Comments & Summary | The focus of this iteration was to create a restful web api to store a collection of all the user’s submitted notes. Additional functionality was also added to existing features with regular expressions allowing for partial solutions on pre-made note quizzes
Iteration #7
2023 Apr 16th
Features in scope | User note modification | Wordnet functionality for synonyms | Time based quiz scoring | User account settings | Selenium tests | Detailed scoring system | Android client
Features implemented | User note modification | Wordnet functionality for synonyms | Time based quiz scoring | User account settings | Selenium tests | Detailed scoring system
Features in deficit this Iteration | Android client
Iteration Comments & Summary | In this iteration functionality was added to allow notes to be modified after a quiz and then stored to the user’s account, this feature has also been reused to allow users to start tracking progress on the static pre-made notes. The restful web api was updated to allow time tracking of notes. This allows additional functionality to prevent notes from being progressed too fast and encourages users to space out their study. An additonal feature was added that allows users to see the progress on individual questions in their notes. This new system will also skip notes that have been perfected. This is unless the notes are 100% learned off in which case the behaviour will reset. A large part of this iteration has also seen many fixes to existing functionality and testing with selenium
Iteration #8
2023 Apr 30th
Features in scope | Data visualisation of learning progress | Azure SQL database (web API) | Mobile client communication with cloud and API
Features implemented | Data visualisation of learning progress | Azure SQL database (web API) | Mobile client communication with cloud and API
Features in deficit this Iteration
Iteration Comments & Summary | For the final iteration many fixes have been added after more testing of the project. The web API has been updated to store more data on when the users completes learning sessions and uses this information on a chart in the client. The web API now communicates with an SQL database server hosted with azure.