## Sheet1
Iteration #1	Feature	Feature	Feature	Feature
2022 Oct 3rd
Features in scope	Start a quiz	Create a document	Upload document
Features implemented	Start a quiz	Create a document
Features in deficit this Iteration	Upload document
Iteration Comments & Summary	Quiz functionality has been implement on client side, however communication between client and server is not yet set up. All features in this iteration are to be refined in future iterations.

Iteration #2
2022 Dec 3rd
Features in scope	Start a quiz	Review Document	Create a document	Upload document	User account creation
Features implemented	Start a quiz	Review Document
Features in deficit this Iteration	Create a document	Upload document	User account creation
Iteration Comments & Summary	For this iteration I have focused on moving to the Blazor framework for the project.

Iteration #3
2023 Dec 18th
Features in scope	Document creation	User account creation
Features implemented
Features in deficit this Iteration	Document creation	User account creation
Iteration Comments & Summary	Iteration focused on problem solving existing code

Iteration #4
2023 Feb 12th
Features in scope	Android client	Web api (User file store)
Features implemented
Features in deficit this Iteration	Android client	Web api (User file store)
Iteration Comments & Summary	This iteration aims have been to create an android client which is still on going. Beyond this a web api for users to sign in on both clients which will later allow for file storage.

Iteration #5
2023 Mar 5th
Features in scope	User account CRUD	Synonym API functionality	Translation API functionality	Additional quiz functionality (Regex)	Restful API for user files	Android client
Features implemented	User account CRUD	Synonym API functionality	Translation API functionality	Additional quiz functionality (Regex)	Restful API for user files
Features in deficit this Iteration	Android client
Iteration Comments & Summary	For this iteration many features have been introduced to improve the web-client functionality. The android client has been improved and can now complete some of the basic functions seen in the web-client. A new Restful API has been created to allow users to store custom notes.

Iteration #6
2023 Mar 26th
Features in scope	Regex partial solutions	Restful web service (user notes)	User notes CRUD (with restful service)	User note progress tracking
Features implemented	Regex partial solutions	Restful web service (user notes)	User notes CRUD (with restful service)	User note progress tracking
Features in deficit this Iteration
Iteration Comments & Summary	The focus of this iteration was to create a restful web api to store a collection of all the user’s submitted notes. Additional functionality was also added to existing features with regular expressions allowing for partial solutions on pre-made note quizzes

Iteration #7
2023 Apr 16th
Features in scope	User note modification	Wordnet functionality for synonyms	Time based quiz scoring	User account settings	Selenium tests	Detailed scoring system	Android client
Features implemented	User note modification	Wordnet functionality for synonyms	Time based quiz scoring	User account settings	Selenium tests	Detailed scoring system
Features in deficit this Iteration	Android client
Iteration Comments & Summary	In this iteration functionality was added to allow notes to be modified after a quiz and then stored to the user’s account, this feature has also been reused to allow users to start tracking progress on the static pre-made notes. The restful web api was updated to allow time tracking of notes. This allows additional functionality to prevent notes from being progressed too fast and encourages users to space out their study. An additonal feature was added that allows users to see the progress on individual questions in their notes. This new system will also skip notes that have been perfected. This is unless the notes are 100% learned off in which case the behaviour will reset. A large part of this iteration has also seen many fixes to existing functionality and testing with selenium

Iteration #8
2023 Apr 30th
Features in scope	Data visualisation of learning progress	Azure SQL database (web API)	Mobile client communication with cloud and API
Features implemented	Data visualisation of learning progress	Azure SQL database (web API)	Mobile client communication with cloud and API
Features in deficit this Iteration
Iteration Comments & Summary	For the final iteration many fixes have been added after more testing of the project. The web API has been updated to store more data on when the users completes learning sessions and uses this information on a chart in the client. The web API now communicates with an SQL database server hosted with azure.